## Sheet1
(HWA) RISK ASSESSMENT
Risk ID | Date registered | Risk area | Risk description | Probability |  |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 2021-05-27 | SQL Connection Failure | Not being to access database to stored and retrieve data |  | x |  |  |  | x | Failure connection will hinder the implementation of my project | Depends on what kind of database failure | Contact supervisors or search for solution via internet.
2 | 2021-05-27 | Computer Virus | Not being able to files required for project |  | x |  |  | x |  | Viruses infect and corrupt data on system, so potential formating of data could be required to much level | 1-2 days depening on virus damage | Use antivirus to locate and remove from system
3 | 2021-05-27 | Power Outage | Not being able to use computer to work on project | x |  |  |  |  | x | Will have a massive impact as no power means no access to any terminal | Depends on when the council orchestrate solution | Use my reminaing phone battery to make contact with supervisior regarding situation
4 | 2021-05-27 | Computer Hacked | Can be targetting by a hacker who could possibly corrupt system flies if not delete important files | x |  |  |  |  | x | Depending on the damage the hacker causes has the potential to be wiped all data and steal personal data | 1-3 Days | for mat and re-setup pc and couble check pc
5 | 2021-05-27 | RSI - repetitive strain injury | Carpal tunnel syndrome, eye strain from blue light. Pain can range from mild severe |  |  | x | x |  |  | Slower movements and more rest time | Depends on how bad the condition is | Inform supervisor and see doctor to get diagosed and get prescribed medcine.
6 | 2021-05-27 | Covid-19 (Pandemic) | Being severely ill after getting covid-19 |  | x |  |  |  | x | Will hinder my progress on the project as my health will be affected . | Governemnt guildlines suggest 7-14days for symptoms to run its course. If condition worsen contact emergency services for full diagosed and treatment. | Inform and keep supervisor updated with condition, and take precaution (self-isolate)